## Roles
Person | Owns Primary Feature | Module Responsible | Secondary Feature | Competencies | Responsible | Role name
S1 | CC/EBA | Control PID | OTA | STM Dev/CARLA | Marco | Control Engineer
S2 | ACC | Control MPC + LL | TSF | Rasp Dev/STM | Joao | Embedded Engineer
S3 | TSR | Perception | Cluster | Rasp Dev/QT | Hugo | AI/ML and UI Engineer
S4 | LKA | Perception | Testing | Rasp Dev | Bruno | Perception Engineer
S5 | Infrastructure | Comms, LL | OTA | Rasp Dev/STM | Rui | Infra Engineer
Primary Feature Owner: Each person is responsible for the end-to-end delivery of a feature, and should create a strategy for each feature to be achieved.
Subdividir LKA?
Competency: Each person implements features at their specified competency level, as per request of the feature owner. | [6 empty] | Owner primeiramente responsável pela definição de requisitos
Secondary feature: Each person has a secondary feature he is responsible for when the primary feature isn't being worked on.

## GANNT
Feature | Tasks | Phase 1 | [5 empty] | Phase 2
|  | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
LKA | Lane Detection Research | bar: Phase 1 W3
| Pick Lane Detection Architecture - ADR | Phase 1 W4: ALL
Implement Lane Detection in Perception Module | bar: Phase 1 W4
Implement Path Planning with Perception output | bar: Phase 1 W5
Integrate Accelerometer | bar: Phase 1 W3
MCP Controller Implementation | bar: Phase 1 W5
| Control Architecture - ADR | Phase 1 W7: ALL
| Lap Test (LKA + CC) | Phase 1 W8: TEST
CC | PID Controller Implementation | bar: Phase 1 W3
| Cruise Control Test - maintaining speed without LKA | Phase 1 W5: TEST
Integrate PID with Path-Planning | bar: Phase 1 W8
ACC Research | bar: Phase 1 W6
ACC Integration with Perception | bar: Phase 2 W9 to Phase 2 W11
| Test car maintains a safety distance to vehicle in front | Phase 2 W12: TEST
Infrastructure | HAILO/CAM AGL Pipelines | bar: Phase 1 W3
Setup CARLA w/ sensors | bar: Phase 1 W3
Camera feed from CARLA | bar: Phase 1 W3
EBA | EBA Research: object detection model survey | bar: Phase 1 W8
Integrate Distance sensor | bar: Phase 1 W7
Object detection interface with Control | bar: Phase 2 W9
| Test Car avoids objects at a distance less than safety distance | Phase 2 W11: TEST
TSR | Research GEN AI for data augmentation during TSR and EBA model training | bar: Phase 1 W7
| Object and Sign Detection Model ADR | Phase 1 W8: ALL
TSR dataset prep (GTSRB); model training started | bar: Phase 2 W9
| Test decision-making on Traffic Signs | Phase 2 W12: TEST
UI | UI/UX Improvements | bar: Phase 1 W4
QT UI for traffic sign and obstacle detection | bar: Phase 2 W10

## Scenario 2
Feature | Tasks | Phase 1 | [5 empty] | Phase 2
|  | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
LKA | Lane Detection Research | bar: Phase 1 W3
| Pick Lane Detection Architecture - ADR | Phase 1 W4: ALL
Implement Lane Detection in Perception Module | bar: Phase 1 W4
Implement Path Planning with Perception output | bar: Phase 1 W5
Integrate Accelerometer | bar: Phase 1 W3
MCP Controller Implementation | bar: Phase 1 W5
| Control Architecture - ADR | Phase 1 W7: ALL
| Lap Test (LKA + CC) | Phase 1 W8: TEST
CC | PID Controller Implementation | bar: Phase 1 W3
| Cruise Control Test - maintaining speed without LKA | Phase 1 W5: TEST
Integrate PID with Path-Planning | bar: Phase 1 W8
ACC Research | bar: Phase 1 W6
ACC Integration with Perception | bar: Phase 2 W9 to Phase 2 W11
| Test car maintains a safety distance to vehicle in front | Phase 2 W12: TEST
Infrastructure | HAILO/CAM AGL Pipelines | bar: Phase 1 W3
Setup CARLA w/ sensors | bar: Phase 1 W3
Camera feed from CARLA | bar: Phase 1 W3
EBA | EBA Research: object detection model survey | bar: Phase 1 W8
Integrate Distance sensor | bar: Phase 1 W7
Object detection interface with Control | bar: Phase 2 W9
| Test Car avoids objects at a distance less than safety distance | Phase 2 W11: TEST
TSR | Research GEN AI for data augmentation during TSR and EBA model training | bar: Phase 1 W7
| Object and Sign Detection Model ADR | Phase 1 W8: ALL
TSR dataset prep (GTSRB); model training started | bar: Phase 2 W9
| Test decision-making on Traffic Signs | Phase 2 W12: TEST
UI | UI/UX Improvements | bar: Phase 1 W4
QT UI for traffic sign and obstacle detection | bar: Phase 2 W10